{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":21,"n_cols":9,"rows_kept":21,"cut":false,"hidden":false,"merged":[[0,0,0,8],[1,0,1,8],[2,1,2,8],[3,1,3,8],[4,1,4,8],[5,1,5,3],[5,5,5,8],[6,0,6,8],[7,1,7,3],[8,1,8,3],[9,1,9,3],[10,1,10,3],[12,0,12,8],[13,1,13,4],[13,5,13,7],[11,1,11,3],[14,1,14,4],[14,5,14,7],[15,1,15,4],[15,5,15,7],[16,1,16,4],[16,5,16,7],[17,1,17,4],[17,5,17,7],[18,0,18,8],[19,1,19,6],[20,1,20,6]]}
["XX项目V1.0.0.00测试报告"]
["项目描述"]
["测试人员","王铭哲"]
["开发人员","汪荣兵"]
["测试周期","2021/7/7---2021/7/9"]
["是否延期","否",null,null,"延期原因","无"]
["测试进度"]
["序号","内容",null,null,"类别","执行进度","计划完成时间","实际完成时间","备注"]
[1,"概览页面客户人数与数据库不符合",null,null,"BUG",1,"2021-07-08","2021-07-08"]
[2,"使用模板导出列数据有缺失",null,null,"BUG",1,"2021-07-07","2021-07-07"]
[3,"基金详情页收益率只有一个时间点时未做展示",null,null,"BUG",1,"2021-07-07","2021-07-07"]
[4,"基金详情页切换基准置灰的问题",null,null,"BUG",1,"2021-07-01","2021-07-01"]
["BUG信息"]
["分类","数量",null,null,null,"责任人",null,null,"备注"]
["Bug总数",4,null,null,null,"汪荣兵",null,null,"已解决"]
["待解决",0]
["待验证",0]
["需要紧急解决"]
["风险"]
["序号","风险描述",{"$nulls":5},"状态","等级"]
[1,"登陆界面暂不支持",{"$nulls":5},"持续观察","高"]